## Estimation
Estimation for Course Management System Testing (TCT)
Assumption
100% | This is the rough estimation based on the quality index of + S/W・H/W Combination test (TCT): 20.00 [Item /KL] We will re-estimate after receiving the new quality index for the project as well as the TCT test spec. from Customer..
200% | Assume that the Test specification released from Customer has been defined both functional and non-functional test cases.
Items |  |  | Effort (man-hours)
| 100% | Total effort for test preparation and execution test |  | 1700.8292
| 200% | Total effort for Project Management |  | 170.0829
| 300% | Total effort |  | 1870.9121
| 400% | Duration (months) |  | 2
Schedule
| Å | Start date
| Å | End date
Effort distribution (for each phase) |  |  | Effort | %
| 100% | Test Initiation | 39.3333 | 2.102%
| 200% | Test Planning | 36 | 1.924%
| 300% | Test case development | 228.4722 | 12.21%
| 400% | Test Environment Setup | 0 | 0%
| 500% | Test Execution | 1070.4167 | 57.21%
| 600% | Bug Report and Verification | 107.0417 | 5.721%
| 700% | Regression Testing | 0 | 0%
| 800% | Prepare Test Report | 64.9444 | 3.471%
| 900% | Risk management | 154.6208 | 8.264%
| 1000% | Test management | 170.0829 | 9.091%
Testing Activities & Estimation |  |  | Effort (man-hours) |  | Estimated effort (man-hours) |  |  | Remarks
# |  |  |  |  | Best | Most likely | Worst
100% | Test Initiation |  | 39.3333
|  | Study Requirements, Q&A |  | 39.3333 | 32 | 40 | 44
200% | Test Planning |  | 36
|  | Develop test strategy, test methodology |  | 8 | 6 | 8 | 10
|  | Develop detailed test plan |  | 20 | 18 | 20 | 22
|  | Develop test schedule |  | 8 | 6 | 8 | 10 | TCT Duration for our scope: TCT(2019/11/1～2019/12/27)
300% | Test case development |  | 228.4722
| 175000% | Total estimated test cases (TCT) | [5 empty] | Based on quality index of the existing systems + S/W・H/W Combination test (TCT): 20.00 [Item /KL]
|  | Write test cases |  | 0 | 0 | 0 | 0
|  | Design test data, input data |  | 0 | 0 | 0 | 0
|  | Review test case, update test case |  | 0 | 0 | 0 | 0
|  | Study/update the test cases and prepare data if needed |  | 0.13056 | 0.083333 | 0.13333 | 0.16667
400% | Test Environment Setup |  | 0
|  | Software (all parts deployment) |  | 0 | 0 | 0 | 0 | T.B.D
|  | Devices (all server PC setup) |  | 0 | 0 | 0 | 0 | T.B.D
|  | Stubs if needed |  | 0 | 0 | 0 | 0 | T.B.D
500% | Test Execution |  | 1070.4167
|  | The first Test Round |  | 708.75 | 577.5 | 700 | 875 | Based on real quality index for previous TCT phase + Test Execution Productivity: 20 TCs / 1 day
|  | The half of second Test Round (include Regression Test) |  | 361.6667 | 315 | 367.5 | 385
600% | Bug Report and Verification |  | 107.0417
|  | Bug report and bug verification (10% of Test Execution) |  | 107.0417 | 96.3375 | 107.0417 | 117.7458
700% | Regression Testing |  | 0
|  | Regression Test (20% of a round) |  | 0 | 0 | 0 | 0 | It is performed along with The Second Test Round.
800% | Prepare Test Report |  | 64.9444
|  | 5% of test execution (including all activities related to test report) |  | 64.9444 | 64.9444 | 64.9444 | 64.9444
Provide status (weekly/daily) reports, including risks and issues; and attend status meetings
900% | Risk management |  | 154.6208
|  | 10% |  | 154.6208
1000% | Test management |  | 170.0829
|  | 10% |  | 170.0829
|  | Total (man-day) |  | 1870.9121

## Estimation_HotelBooking
Estimation for Hotel booking Management System Testing (TCT)
Assumption
100% | This is the rough estimation based on the quality index of + S/W・H/W Combination test (TCT): 20.00 [Item /KL] We will re-estimate after receiving the new quality index for the project as well as the TCT test spec. from Customer..
200% | Assume that the Test specification released from Customer has been defined both functional and non-functional test cases.
Items |  |  | Effort (man-hours)
| 100% | Total effort for test preparation and execution test |  | 2509.3292
| 200% | Total effort for Project Management |  | 250.9329
| 300% | Total effort |  | 2760.2621
| 400% | Duration (months) |  | 2
Schedule
| Å | Start date
| Å | End date
Effort distribution (for each phase) |  |  | Effort | %
| 100% | Test Initiation | 39.3333 | 1.425%
| 200% | Test Planning | 36 | 1.304%
| 300% | Test case development | 928.4722 | 33.64%
| 400% | Test Environment Setup | 0 | 0%
| 500% | Test Execution | 1070.4167 | 38.78%
| 600% | Bug Report and Verification | 107.0417 | 3.878%
| 700% | Regression Testing | 0 | 0%
| 800% | Prepare Test Report | 99.9444 | 3.621%
| 900% | Risk management | 228.1208 | 8.264%
| 1000% | Test management | 250.9329 | 9.091%
Testing Activities & Estimation |  |  | Effort (man-hours) |  | Estimated effort (man-hours) |  |  | Remarks
# |  |  |  |  | Best | Most likely | Worst
100% | Test Initiation |  | 39.3333
|  | Study Requirements, Q&A |  | 39.3333 | 32 | 40 | 44
200% | Test Planning |  | 36
|  | Develop test strategy, test methodology |  | 8 | 6 | 8 | 10
|  | Develop detailed test plan |  | 20 | 18 | 20 | 22
|  | Develop test schedule |  | 8 | 6 | 8 | 10 | TCT Duration for our scope: TCT(2019/11/1～2019/12/27) | 30%
300% | Test case development |  | 928.4722
| 175000% | Total estimated test cases (TCT) | [5 empty] | Based on quality index of the existing systems + S/W・H/W Combination test (TCT): 20.00 [Item /KL]
|  | Write test cases |  | 0.4 | 0.3 | 0.4 | 0.5
|  | Design test data, input data |  | 0 | 0 | 0 | 0
|  | Review test case, update test case |  | 0 | 0 | 0 | 0
|  | Study/update the test cases and prepare data if needed |  | 0.13056 | 0.083333 | 0.13333 | 0.16667
400% | Test Environment Setup |  | 0
|  | Software (all parts deployment) |  | 0 | 0 | 0 | 0 | T.B.D
|  | Devices (all server PC setup) |  | 0 | 0 | 0 | 0 | T.B.D
|  | Stubs if needed |  | 0 | 0 | 0 | 0 | T.B.D
500% | Test Execution |  | 1070.4167
|  | The first Test Round |  | 708.75 | 577.5 | 700 | 875 | Based on real quality index for previous TCT phase + Test Execution Productivity: 20 TCs / 1 day
|  | The half of second Test Round (include Regression Test) |  | 361.6667 | 315 | 367.5 | 385
600% | Bug Report and Verification |  | 107.0417
|  | Bug report and bug verification (10% of Test Execution) |  | 107.0417 | 96.3375 | 107.0417 | 117.7458
700% | Regression Testing |  | 0
|  | Regression Test (20% of a round) |  | 0 | 0 | 0 | 0 | It is performed along with The Second Test Round.
800% | Prepare Test Report |  | 99.9444
|  | 5% of test execution (including all activities related to test report) |  | 99.9444 | 99.9444 | 99.9444 | 99.9444
Provide status (weekly/daily) reports, including risks and issues; and attend status meetings
900% | Risk management |  | 228.1208
|  | 10% |  | 228.1208
1000% | Test management |  | 250.9329
|  | 10% |  | 250.9329
|  | Total (man-day) |  | 2760.2621

## WBS
Estimate for Course Management System
Summary
| Standard | Working hours per day |  | 8
|  | Working days per month |  | 20
|  | Working hours per function point (FP) |  | 9
| Project | Total efforts in man-day unit |  | 45.5417
|  | Total efforts in man-month unit |  | 2.28
|  | Project size in FP unit |  | 41
|  | Productivity (KLOC/man-month) |  | #REF!
|  | Development duration (months) |  | 1
Schedule
| Å | Start date |  | 2020-03-02
| Å | Beta release |  | 2020-03-17
| Å | Final release |  | 2020-03-27
| Å | Finish acceptance test |  | 2020-03-30
Effort distribution
|  | Item | Effort | %
| 100% | Preparation | 3.6667 | 8.051%
| 200% | Requirement | 3 | 6.587%
| 300% | Design | 3.75 | 8.234%
| 400% | Implementation (Code - UT - Review) | 16.625 | 36.51%
| 500% | Test (CT test and fix bug) | 11 | 24.15%
| 600% | Build and release | 3.5 | 7.685%
| 700% | Acceptance test support | 4 | 8.783%
Work Breakdown Structure & Estimate |  |  |  |  | Estimated effort
# | Activities |  |  | Expected | Best | Most likely | Worst
|  |  |  | (man-days) | (man-days) | (man-days) | (man-days)
100% | Preparation |  | 3.6667
| 110% | Development Environment
|  | Prepare Development Environment (Linux OS, dependencies, user, directory, version control, branching plan ...) |  | 1.4167 | 1 | 1.5 | 1.5
| 120% | Testing Environment
|  | Prepare Runtime Environment (Windows/Linux OS, dependencies, user, directory ...) |  | 1.25 | 1 | 1.25 | 1.5
| 130% | DevOps
|  | Process to build, run UT, deploy |  | 0.5 | 0.5 | 0.5 | 0.5
|  | Process to run static check by Sonar |  | 0.5 | 0.5 | 0.5 | 0.5
200% | Requirement |  | 3
| 210% | Requirement specifications
|  | Follow up to confirm requirement specifications in Q&A list |  | 0.5 | 0.5 | 0.5 | 0.5
| 220% | Libraries for C++
|  | Select and intergrate OSS Poco library for implementation |  | 0.5 | 0.5 | 0.5 | 0.5
| 230% | AI Framework
|  | Build Caffe, load trained model |  | 2 | 1.5 | 2 | 2.5
300% | Design |  | 3.75
Function specification
|  | Overview |  | 0.5 | 0.5 | 0.5 | 0.5
|  | Precondition and scope of application |  | 0.5 | 0.5 | 0.5 | 0.5
|  | Function |  | 1.25 | 1 | 1.25 | 1.5
|  | Interface |  | 0.75 | 0.5 | 0.75 | 1
|  | Format of data |  | 0.75 | 0.5 | 0.75 | 1
400% | Implementation (Code - UT - Review) |  | 16.625
| 410% | Modules used by both Client Application and Server Application
| a | Data validation
|  | IP Address, Port |  | 0.5 | 0.5 | 0.5 | 0.5
|  | Image |  | 1 | 0.5 | 1 | 1.5
| b | Socket communication
|  | Socket connection (open, close, send, receive) |  | 1.0417 | 0.75 | 1 | 1.5
|  | Data Communication |  | 1.25 | 1 | 1.25 | 1.5
| c | Configuration |  | 1.0417 | 0.75 | 1 | 1.5
| d | Logging Utility |  | 1.0417 | 0.75 | 1 | 1.5
| 420% | Client Application
| a | Image manipulation
|  | Draw rectangle on the image |  | 1.25 | 1 | 1.25 | 1.5
| b | Main work-flow
|  | Handle main work flow |  | 1.25 | 0.75 | 1.25 | 1.75
| 430% | Server Application
| a | Communication for AI Framework interface
|  | Connection |  | 1.25 | 1 | 1.25 | 1.5
|  | Data communication |  | 1.25 | 1 | 1.25 | 1.5
| b | Main work-flow
|  | Handle main work-flow |  | 1.75 | 1.5 | 1.75 | 2
| c | JSON manipulation
|  | Build, parse JSON format |  | 1.5 | 1 | 1.5 | 2
| 440% | AI Framework External Interface
|  | Write Python program to implement Caffe external interface |  | 2.5 | 2 | 2.5 | 3
500% | Test (CT test and fix bug) |  | 11
| 510% | CT test plan and Test case
|  | Develop CT test case |  | 3 | 2.5 | 3 | 3.5
| 520% | Execute test and fix bug
|  | Round #1 |  | 4 | 3 | 4 | 5
|  | Round #2 |  | 4 | 3 | 4 | 5
600% | Build and release |  | 3.5
| 610% | User manual
|  | Review and update documents for release |  | 1.5 | 1 | 1.5 | 2
| 620% | Setup and build Docker
|  | Setup, build and deploy Docker image |  | 2 | 1.5 | 2 | 2.5
700% | Acceptance test support |  | 4
|  | 2 persons which 25% effort in 2 days |  | 4
|  | Total (man-day) |  | 45.5417

## QualityIndexValue
■Course Management System development quality index value
Phase/ |  |  | Course Management System development
| Deliverables | Item | Planned value |  | Value |  |  | <Development KL> | Attachment1_CommonizationKLD.xlsx
Development scale | [8 empty] | Maintenance terminal device | Central control device | Base station control device (MCP9 | Common PF
| Scale | KLOC |  |  | 50 | [KL] |  | New conversion
Requirement analysis
| TCT specification | Test density | 25 | [Item /KL] | 1250 | [Item] |  | 800% | Item /Page
|  | Document density | 3.125 | [Page /KL] | 156.25 | [Page]
|  | Review density | 0.08 | [Hr /Item] | 100 | [Hr]
|  | Error detection density | 0.15 | [Record /Item] | 187.5 | [Record]
External design (BD)
| External specification | Document density | 4 | [Page /KL] | 200 | [Page]
|  | Review density | 0.52 | [Hr /Page] | 104 | [Hr]
|  | Error detection density | 0.98 | [Record /Page] | 196 | [Record]
| SCT specification | Test density | 35 | [Item /KL] | 1750 | [Item]
|  | Document density | 4.375 | [Page /KL] | 218.75 | [Page]
|  | Review density | 0.07 | [Hr /Item] | 122.5 | [Hr]
|  | Error detection density | 0.11 | [Record /Item] | 192.5 | [Record]
Internal design (DD)
| Internal specification | Document density | 8 | [Page /KL] | 400 | [Page]
|  | Review density | 0.31 | [Hr /Page] | 124 | [Hr]
|  | Error detection density | 0.51 | [Record /Page] | 204 | [Record]
| UT specification | Test density | 80 | [Item /KL] | 4000 | [Item] |  | 1900% | Item /Page
|  | Document density | 4.2105 | [Page /KL] | 210.5263 | [Page]
|  | Review density | 0.04 | [Hr /Item] | 160 | [Hr]
|  | Error detection density | 0.04 | [Record /Item] | 160 | [Record]
Production (CD)
| Code creation | Review density | 1.95 | [Hr/KL] | 97.5 | [Hr]
|  | Error detection density | 6.49 | [Record/ KL] | 324.5 | [Record]
Unit test (UT)
| UT result report | Test density | 100 | [Item /KL] | 5000 | [Item]
|  | Error detection density | 3.8 | [Record/ KL] | 190 | [Record]
S/W Combination test (SCT)
| SCT result report | Test density | 35 | [Item /KL] | 1750 | [Item]
|  | Error detection density | 1.9 | [Record/ KL] | 95 | [Record]
S/W・H/W Combination test (TCT)
| TCT result report | Test density | 20 | [Item /KL] | 1000 | [Item] | TCT1 only
|  | Error detection density | 0.95 | [Record/ KL] | 47.5 | [Record] | TCT1 only
After shipment (ST～)
|  | Residual error | 0.2 | [Record/ KL] | 10 | [Record]

## DetailTasks_CourseMng
Type of Req. | Main Use-cases | Sub-function list |  | Estimate the num. of test cases |  |  | Details
|  |  |  | Best | Most likely | Worst
Functional List | Creating Courses | 3.2.1.1 Integration with registration system: The system shall periodically upload the latest registrar’s classes list to determine courses that offered in the current semester.
3.2.1.2 The system shall generate course for each class that registered and determine the current set of students that enrolled in that class
3.2.1.3 The system shall allow course instructor to update course content
| Grade Management | 3.2.2.1 Allow grades to be entered online: The system shall allow instructors to enter and modify grades online.
3.2.2.2 Allow students to access their grades online: The system shall allow student to log in their account and check their grades at any time.
3.2.2.2 Allow students to access their grades online: The system shall allow student to log in their account and check their grades at any time.
3.2.2.4 Track and Handle Re-grade Requests: The system shall be able to track and handle requests for re- grades, and all information about re-grades shall be available to the student, and the course instructor.
| Homework Submissions | 3.2.3.1 Accept submissions in multiple formats: The system shall accept submissions in multiple formats, including .zip, .cpp , .txt, .doc, etc.
2.3.2 Support for late submissions: The system shall provide information about late submissions, and also disallow submissions after a certain period of time.
UC_Upload Solution Of Homework Submission
3.2.3.3 Integration with grade management: The homework submission system shall be integrated with the grade management by using online grading templates that can be filled out, and automatically annotating code with line numbers
3.2.3.3.1 assignment grades can be automatically posted to student account.
3.2.3.3.2 grader comments can be sent along with the grades
UC_Evaluating Student’s Homework Submissions Online.
| Group Management | 3.2.4.1 Ability to create groups: The system shall allow students to automatically create groups, and enforce certain conditions such as each student should be a member of exactly one group for a given project.
UC_Create Group
3.2.4.2 Integration with homework submissions: The system shall be able to accept group homework submissions.
3.2.4.3 Integration with grade management: The system shall support grade management for groups, and track how the group grade translates into individual student grades.
UC_Evaluating Group’s Homework Submissions Online.
3.2.4.4 Group Maintenance: Invariably, students either switch groups, or drop out from a group altogether. The system shall support such transitions and keep track of them.
| Online Quizzes | 3.2.5.1 The system shall instructor to upload quizzes.
3.2.5.2 The system shall allow instructor to upload answer key to the system.
3.2.5.3 The system shall allow student to answer quizzes.
3.2.5.4 The system shall compare answer key with student answer.
3.2.5.5 Integration with grade management: the system manage the quizzes’ grades by sending it to grade management in order to allow instructor to modify the grades and student to see their grades.
UC_Answer online Quizzes
| Create Accounts | 3.2.6.1 The system shall automatically create accounts for each class.
3.2.6.1.1 Create one account for course instructor regardless to the number of classes that he/she teach.
3.2.6.1.2 The account username is course name and its number.
3.2.6.1.3 The account password is the same password that in AIS.
3.2.6.1.4 Any change in the password in AIS the system shall reflect it on the instructor account password in CMS.
3.2.6.1.5 Create one account for each student that registered in this class.
3.2.6.1.6 The account username is course name and its number.
3.2.6.1.7 The account password is the same password that in SIS.
3.2.6.1.8 Any change in the password in SIS the system shall reflect it on the student account password in CMS.
Non-Functional List | Response time |  | Average response time shall be less than 2 second | 5000% | 4000% | 3000% | List out all APIs that system supports e.g. 1. login API 2. logout API 3. requestcreatingcouse API 4. requestcourselist API 5. requestsubmithomework API 6. requestviewgrade API 7. requestdeletecouse API etc
| Throughput |  | The system shall accommodate 1000 booked per minute | 600% | 400% | 300% | less than 1000 booked 1000 booked more than 1000 booked
| Recovery Time |  | In case of a system failure, redundant system shall resume operations within 30 seconds. Average repair time shall be less than 1 hour. | 1000% | 800% | 600% | switch from Active to Standby Switch from standby to Active Failed to switch There are about 1000 booked at the time of switching There are about 4000 book at the time of swtiching No user at the time of switching
| Start-up/Shutdown Time |  | The system shall be operational within 1 minute of starting-up | 1500% | 1200% | 800% | Starting up of Active system Starting up of Standby system Shutting down of Active system Shutting down of Standby system Shutting down when there are 1000 users used Shutting down when there are 4000 users used Shutting down while having online couses Shutting down while having homework submission etc
| Capacity |  | The system accommodate 4000 concurrent users. | 400% | 300% | 200% | max 4000 users more than 4000 users
| Utilization of Resources |  | The system shall store in the database no more than one million transactions. If the database grows over this limit, old transaction shall be backed up and deleted from the operational database. | 1000% | 700% | 500% | zero transactions 999999 transactions 1,000, 000 transactions 1,000,0001 transactions 2,000,000 transactions
| Security |  | Firewall Protection: The course management software system shall run inside a firewall. |  |  | 200%
Support different roles: The system shall support different roles for users, such as Instructors, Students, and administrative staff, the user logged in with given role should only be allowed access consistent with that role. For example a student shall only be allowed to see he/she grades not to modify it.
reliability
Scalability

## DetailTasks_HotelBooking
Type of Req. | Main Use-cases | Sub-function list |  | Estimate the num. of test cases |  |  | Details
|  |  |  | Best | Most likely | Worst
GUI | top panel |  |  | 500% | 400% | 300%
| search panel |  |  | 5000% | 4000% | 3000%
| right panel | view hotel |  | 2000%
detais booking
|  | payment |  | 10000% | 9000% | 8000%
other detail panel
Functional List | UC Search room
|  |  |  | 5000% | 4000% | 3000%
|  | view hotel |  | 2000%
detais booking
|  | payment |  | 10000% | 9000% | 8000%
other detail panel
Non-Functional List | Response time |  | Average response time shall be less than 2 second | 1500% | 1000% | 700% | List out all APIs that system supports e.g. 1. login API 2. logout API 3. requestcreatingcouse API 4. requestcourselist API 5. requestsubmithomework API 6. requestviewgrade API 7. requestdeletecouse API etc
| Throughput |  | The system shall accommodate 1000 booked per minute | 600% | 400% | 300% | less than 1000 booked 1000 booked more than 1000 booked
| Recovery Time |  | In case of a system failure, redundant system shall resume operations within 30 seconds. Average repair time shall be less than 1 hour. | 1000% | 800% | 600% | switch from Active to Standby Switch from standby to Active Failed to switch There are about 1000 booked at the time of switching There are about 4000 book at the time of swtiching No user at the time of switching
| Start-up/Shutdown Time |  | The system shall be operational within 1 minute of starting-up | 1500% | 1200% | 800% | Starting up of Active system Starting up of Standby system Shutting down of Active system Shutting down of Standby system Shutting down when there are 1000 users used Shutting down when there are 4000 users used Shutting down while having online couses Shutting down while having homework submission etc
| Capacity |  | The system accommodate 4000 concurrent users. | 400% | 300% | 200% | max 4000 users more than 4000 users
| Utilization of Resources |  | The system shall store in the database no more than one million transactions. If the database grows over this limit, old transaction shall be backed up and deleted from the operational database. |  |  |  | zero transactions 999999 transactions 1,000, 000 transactions 1,000,0001 transactions 2,000,000 transactions
| Security |  | Firewall Protection: The course management software system shall run inside a firewall. |  |  | 200%
Support different roles: The system shall support different roles for users, such as Instructors, Students, and administrative staff, the user logged in with given role should only be allowed access consistent with that role. For example a student shall only be allowed to see he/she grades not to modify it.
reliability
Scalability